## Summary-GroupIterationProgress
This report has 1 group iteration progress summary sheet to be filled at the end of each iteration by the team leader, 1 project ontribution sheet to be filled by everyone at the end of the semester, and 1 weekly report sheet per student.
This sheet should be completed by the team leader (or other member in the team) by the end of each iteration.
iteration | Date range | accomplishment summary (such as user stories/tasks completed/big progress, good practices used, etc) | Technical issues summary | non-technical issues summary | Process improvement/plan | # of user story points completed | # of user story points in progress | # of issues opened | # of issues closed | # of issues remained | Total work time (h) | Total Individual work time (h) | Total group meeting time (h) | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | Any other metrics defined in your SPPP
0 | 09/03-09/12 | Project Ideation, Design, and Flow. Implementation of MongoDB, CI/CD Setup. Start Chatbot Implementation. CI/CD Setup, SpringBoot Setup, Postgresql user dbms setup. Wireframe done. Design decision tree for course building implementation. SPPP version 1. Presentation for Iteration 0. Set up test for Git. Lab1 submission. Created first PR for implementation of CICD. | none identified yet | learning new tech stack for some members | Start setting up spring boot, writing the scripts, and working on the project. | 58 | 113 | 24 | 3 | 21 | 52.16 | 39.66 | 2 | 12.45 | 4.3 | 5.16 | #VALUE! | #VALUE! | 4.35 | 4.5
1 | 09/13-09/24
2 | 09/25-10/08
3 | 10/09-10/15

## projectcontribution
This sheet need to be filled by the end of the semester. You should clearly describe your contribution to the group project in each category in the whole semester.
StudentName | SPPP Document | Requirement Analysis on Pivotaltracker | Design Document (SDD) | Testing Documentation (STD) | Presentation | Implementation (code on Github) | Testing (unittest code on Github or manual testing) | Configuration and Deployment | General communication and management | Other Comments
Natasya Liew
Natthaphon Foithong
Ananya Singh
Battal Cevik
Poom Chantarapornrat
YiJun Liu

## Natasya Liew
The sheet shows an example of a student weekly report. Only include the time that you use to work on the project. Each student should make your own sheet to report your work weekly.
Your Lead Roles: Backup Project Leader, requirement leader
Week # | Date range | Total actual time of this week tasks (h) | Total Individual work time | Total group meeting time | Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | Project Deliverable Contribution | Issues | Issue status or plan | Estimated tasks for next week | Total estimated time
1 | 09/03-09/10 | 7 | 6 | 1 | 0 - learn git and django, read several tutorials 1 - define high level requirements, 5 - make project plan, send reminders to team members 6 - set up git 7 - research similar products, prepare presentation | 3 | 1 |  |  |  | 0.5 | 1 | 0.5 | 1. Write 3 sections of SPPP 2. Set up git, commit a test message on git 3. Participate in Iteration 0 presentation | 1. not familar with Django framework, hard to write any code on it 2. communication is not clear. Task assignments is not clear. | 1. finish Django tutorial in 2 weeks, be able to create simple Djano hello world project next week 2. Send task assignments to all members again | 0 - continue to learn Django 1 - continue to define requirements 3 - implement a basic hello world on Django | 6
0 | 09/03-09/12 | 9 | 7 | 2 | 0 - Learn about CI/CD and Llama 2 1 - For the Database and Chatbot Mechanism 2 - For the Database, Decision Tree, and Chatbot Mechanism 3 - For the Database 4 - n/a 5 - Team Creation, Environment Setup, Project Ideation, Work Division 6 - Set up Git 7 - n/a | 2 | 1 | 1 | 2 | 0 | 0.5 | 0.5 | 0 | 1. Team creation and communication 2. Project Ideation 3. Set up git, Gdrive, discord notes 4. Meeting Memo 1 and 2 5. SDD write-up: database design, Decision tree algorithm, and Model and Tools section 6. update README.md file 7. Database Design for MongoDB 8. Database creation (for MSSD program only) in MongoDB 9. Contribute to the SPPP: risk mgmt document 10. Work together with Poom for the decision tree and graph of the course builder mechanism | n/a | 1. Create work tickets 2. finish Database design 3. start Decision Tree implementation 4. code the Chatbot implementation/mechanism in Python 5. Oversee teamwork | 3 - Finish MongoDB database, Decision Tree Implementation, and Chatbot Implementation 4 - Test Database and new implementations 5 - Division of Work to build MVP by iteration 1 | 15
1 | 09/13-09/24
2 | 09/25-10/08
3 | 10/09-10/15

## Ananya Singh
The sheet shows an example of a student weekly report. Only include the time that you use to work on the project. Each student should make your own sheet to report your work weekly.
Your Lead Roles: Backup Project Leader, requirement leader
Week # | Date range | Total actual time of this week tasks (h) | Total Individual work time | Total group meeting time | Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | Project Deliverable Contribution | Issues | Issue status or plan | Estimated tasks for next week | Total estimated time
1 | 05/10-05/16 | 7 | 6 | 1 | 0 - learn git and django, read several tutorials 1 - define high level requirements, 5 - make project plan, send reminders to team members 6 - set up git 7 - research similar products, prepare presentation | 3 | 1 |  |  |  | 0.5 | 1 | 0.5 | 1. Write 3 sections of SPPP 2. Set up git, commit a test message on git 3. Participate in Iteration 0 presentation | 1. not familar with Django framework, hard to write any code on it 2. communication is not clear. Task assignments is not clear. | 1. finish Django tutorial in 2 weeks, be able to create simple Djano hello world project next week 2. Send task assignments to all members again | 0 - continue to learn Django 1 - continue to define requirements 3 - implement a basic hello world on Django | 6
0 | 09/03-09/12 | 7 | 5 | 2 | 0 - learned mermaid syntax to build architecture diagram 2 - Designed the architectural flow for our project 5 - present archtectural plan to the team 6 - set up git and project folder structure 7 - prepare presentation | 2 |  | 2 |  |  | 2 | 2 | 2 | 1. Write 3 sections of SPPP 2. Set up git, commit a test message on git Iteration 0 presentation |  | 1. Start working on the spring boot project 2. Create Databases in Postgres 3. Start looking at implementing security 4. Start building JSON API contracts | 5. Build the initial APIs to call the LLM 6. UI should be able to call the API I built | 6
1 | 09/13-09/24
2 | 09/25-10/08
3 | 10/09-10/15

## Natthaphon Foithong
The sheet shows an example of a student weekly report. Only include the time that you use to work on the project. Each student should make your own sheet to report your work weekly.
Your Lead Roles: Backup Project Leader, requirement leader
Week # | Date range | Total actual time of this week tasks (h) | Total Individual work time | Total group meeting time | Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | Project Deliverable Contribution | Issues | Issue status or plan | Estimated tasks for next week | Total estimated time
1 | 05/10-05/16 | 7 | 6 | 1 | 0 - learn git and django, read several tutorials 1 - define high level requirements, 5 - make project plan, send reminders to team members 6 - set up git 7 - research similar products, prepare presentation | 3 | 1 |  |  |  | 0.5 | 1 | 0.5 | 1. Write 3 sections of SPPP 2. Set up git, commit a test message on git 3. Participate in Iteration 0 presentation | 1. not familar with Django framework, hard to write any code on it 2. communication is not clear. Task assignments is not clear. | 1. finish Django tutorial in 2 weeks, be able to create simple Djano hello world project next week 2. Send task assignments to all members again | 0 - continue to learn Django 1 - continue to define requirements 3 - implement a basic hello world on Django | 6
0 | 09/03-09/12 | 13.16 | 11.16 | 2 | Individual Task Breakdown 0 - Learning git and github, watching several tutorial 1 - Research and analyzed the best option for user experience 2 - Quick design for low fidelity using crazy 8s methological 3 - Implementation UI design mockup and wireframing with high fidelity using Figma 5 - Discord conversation, a meeting participant and presenting mockup design 6 - Setup personal Git/Github environment | 0.45 | 1.3 | 0.16 | 8 | 0 | 0.15 | 0.3 | 0 | Set up Git, commit to add description for Lab-1 and Delivery mockup UI design | Lack communication and need improvement for agile management | More participante in meeting and start frontend environment for project | 0 - Learning React 3 - Implemention Frontend using React and Bootstap 5 - Prepare for presentation | 15
1 | 09/13-09/24
2 | 09/25-10/08
3 | 10/09-10/15

## Battal Cevik
The sheet shows an example of a student weekly report. Only include the time that you use to work on the project. Each student should make your own sheet to report your work weekly.
Your Lead Roles: Backup Project Leader, requirement leader
Week # | Date range | Total actual time of this week tasks (h) | Total Individual work time | Total group meeting time | Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | Project Deliverable Contribution | Issues | Issue status or plan | Estimated tasks for next week | Total estimated time
1 | 05/10-05/16 | 7 | 6 | 1 | 0 - learn git and django, read several tutorials 1 - define high level requirements, 5 - make project plan, send reminders to team members 6 - set up git 7 - research similar products, prepare presentation | 3 | 1 |  |  |  | 0.5 | 1 | 0.5 | 1. Write 3 sections of SPPP 2. Set up git, commit a test message on git 3. Participate in Iteration 0 presentation | 1. not familar with Django framework, hard to write any code on it 2. communication is not clear. Task assignments is not clear. | 1. finish Django tutorial in 2 weeks, be able to create simple Djano hello world project next week 2. Send task assignments to all members again | 0 - continue to learn Django 1 - continue to define requirements 3 - implement a basic hello world on Django | 6
0 | 09/03-09/12 | 9 | 7 | 2 | Individual Task Breakdown 1 - Learned CICD github actions and writing yml file 2 - Research and analyzed the best option for CICD 3 - Created Pull Request for the Github actions 4 - Research on Llama 2 and design implementation 5 - Creating testing plan and automation 6 - Setup personal Git/Github environment 7 - Study and read all materials | 3 | 1 | 0.5 | 0.5 | 1 | 0.2 | 0.2 | 0.6 | 1 - Created first PR for implementation of CICD 2 - Set up git, commit, and finished lab1 as well 3- Actively participated each meetings and decision for the iteration 0 |  |  | 1 - Continue learning CICD 2 - Design automation framework for UI and Backend 3 - Implement basic testng for UI and rest assure library for API
1 | 09/13-09/24
2 | 09/25-10/08
3 | 10/09-10/15

## Poom Chantarapornrat
The sheet shows an example of a student weekly report. Only include the time that you use to work on the project. Each student should make your own sheet to report your work weekly.
Your Lead Roles: Backup Project Leader, requirement leader
Week # | Date range | Total actual time of this week tasks (h) | Total Individual work time | Total group meeting time | Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | Project Deliverable Contribution | Issues | Issue status or plan | Estimated tasks for next week | Total estimated time
1 | 05/10-05/16 | 7 | 6 | 1 | 0 - learn git and django, read several tutorials 1 - define high level requirements, 5 - make project plan, send reminders to team members 6 - set up git 7 - research similar products, prepare presentation | 3 | 1 |  |  |  | 0.5 | 1 | 0.5 | 1. Write 3 sections of SPPP 2. Set up git, commit a test message on git 3. Participate in Iteration 0 presentation | 1. not familar with Django framework, hard to write any code on it 2. communication is not clear. Task assignments is not clear. | 1. finish Django tutorial in 2 weeks, be able to create simple Djano hello world project next week 2. Send task assignments to all members again | 0 - continue to learn Django 1 - continue to define requirements 3 - implement a basic hello world on Django | 6
0 | 09/03-09/12 | 7 | 4.5 | 2.5 | 0 - learn how to use Llama2 in our project, read an article 1 - define first general requirements for the chat bot 2 - draw UML diagrams 5 - participate in the SPPP (requirement section) 6 - set up personal Git/GitHub, set up a requirement tracker tool (GitHub project), and create first user stories | 3 | 1 | 1 | - | - | 0.5 | 1.5 | - | 1. Write the requirement section of the SPPP 2. Set up Git/Github and commit a message to team.md 3. Create UML diagrams for the course reccommendation algorithm and database entities. | 1. not familiar with creating an LLM API, not sure about how to get it work. | 1. Read article and watch YouTube tutorial in a week, be able to find a way to connect the model with a database. | 0 - continue to learn abot Llama2 and HuggingFace API 1 - continue to rehape the requirements as needed 3 - implement the first model API call and test it with the front-end team | 7
1 | 09/13-09/24
2 | 09/25-10/08
3 | 10/09-10/15

## Yujun Liu
The sheet shows an example of a student weekly report. Only include the time that you use to work on the project. Each student should make your own sheet to report your work weekly.
Your Lead Roles: Backup Project Leader, requirement leader
Week # | Date range | Total actual time of this week tasks (h) | Total Individual work time | Total group meeting time | Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | Project Deliverable Contribution | Issues | Issue status or plan | Estimated tasks for next week | Total estimated time
1 | 09/03-09/10 |  | 6 | 1 | 0 - learn git and django, read several tutorials 1 - define high level requirements, 5 - make project plan, send reminders to team members 6 - set up git 7 - research similar products, prepare presentation | 3 | 1 |  |  |  | 0.5 | 1 | 0.5 | 1. Write 3 sections of SPPP 2. Set up git, commit a test message on git 3. Participate in Iteration 0 presentation | 1. not familar with Django framework, hard to write any code on it 2. communication is not clear. Task assignments is not clear. | 1. finish Django tutorial in 2 weeks, be able to create simple Djano hello world project next week 2. Send task assignments to all members again | 0 - continue to learn Django 1 - continue to define requirements 3 - implement a basic hello world on Django | 6
0 | 09/03-09/12 | 7 | 5 | 2 | 0 - learning Spring Boot 2 - backed design 3 - initiated java files 5 - discord conversations | 2 |  | 0.5 | 0.01 |  | 1 |  |  | SPPP write ups(all sections besides 3) | 1. need to learn Spring Boot | 1. go learn it on Youtube 2. practice it with better engineers in the team | 1. coding period 2. some deeper design 3. testing | 6
1 | 09/13-09/24
2 | 09/25-10/08
3 | 10/09-10/15