## Iteration 0
This sheet provides some common risks in student projects. You should check if it applies to your group project. You should also feel free to add other risks. Exemplary analysis is also added.
Risk Category | Risk Title | Description | Estimated likelihood of occurrence (L: 1-5 with 1 lowest likelihood) | Estimated Impact (I:1-5 with 1 lowest impact) | Estimated retirement Cost (C: 1-5 with 1 lowest cost) | Priority (lowest number has high priority) (6-L)*(6-I)*C) | Responsible engineer | Target completion date | Detailed plan | Execution summary | Status
personel | Loss team members | One or more team members drop the class | 2 | 4 | 4 | 4*2*4=32 | team leader and all members | 09/20/2024 | Redefine the project scope if necessary, and assign the tasks to other team members. | No one dropped the class so far | Open
| add new team members | A new team member is assigned to group | 1 | 2 | 1 | 20 | team leader and all members | 09/20/2024 | Redefine the project scope if necessary, and assign the tasks to other team members. | No one added to group so far | Open
| Lack of motivation or responsibility | Team members forgot to communicate and complete their task causing setback to team | 4 | 5 | 5 | 10 | team leader and all members | 10/20/2024 | Communicate to team if you expect to be busy for the upcoming week and need help from other team members to complete your task | Everyone active so far | Open
Communication | duplicate work | Lack of communication and clear work division, causing team members to work on the same thing | 2 | 3 | 2 | 24 | team leader and all members | 10/20/2024 | Communicate to team members on discord on what you are working on, make sure that you are using the cloud files for reports and commit/push changes within 30 minutes intervals. | No duplicated work so far | Open
| worked on wrong components | Worked on something that is not needed or assigned to another team member | 4 | 3 | 3 | 18 | team leader and all members | 10/20/2024 | Communicate to team members on discord on what you are working on or talk to team leaders to make sure that you are on the right track. Buddy up with a team member to make sure that you are progressing correctly | Not a problem as for now | Inactive
| useless work | Work on something that does not progress the project further | 4 | 1 | 1 | 10 | team leader and all members | 10/20/2024 | Communicate to team members on discord on what you are working on or talk to team leaders to make sure that you are on the right track. Buddy up with a team member to make sure that you are progressing correctly | Not a problem as for now | Open
| inconsistent work | Team members can't consistently produce same level of work through the project timeline | 5 | 2 | 1 | 4 | team leader and all members | 10/20/2024 | Communicate to team if you expect to be busy for the upcoming week and need help from other team members to complete your task | Not a problem as for now | Open
Requirements | unclear requirements | Requirements were not clear causing team to repeat work on the task. | 2 | 5 | 5 | 20 | requirement leader | 10/20/2024 | Create a requirements checklist and go through it for every requirement needs. All team members should have the confidence to pushback on unclear or non-relevant requirement | Not a problem as for now | Open
| scope creep | Project's scope increases beyond original plan, this is caused by unclear and poorly defined/controlled scope documentation | 2 | 4 | 3 | 24 | requirement leader | 10/20/2024 | Create a requirements checklist and go through it for every requirement needs. All team members should have the confidence to pushback on unclear or non-relevant requirement | Not a problem as for now | Open
| constant requirements changes | Requirements for task/work keep changing, causing project direction to constantly change | 3 | 5 | 5 | 15 | requirement leader | 10/20/2024 | Only allow requirement changes maximum once within an iteration submission | Not a problem as for now | Open
Management | improper task assignments | Assigning work to team members that can't contribute, unbalance workload among team member, bad foresight on task execution time | 2 | 4 | 3 | 24 | team leader | 10/20/2024 | Team members to pushback if you feel like you are incorrectly assigned task | Everything seems to be progressing well and ahead of schedule | Open
| improper planning | Planning wrong, causing repetition in work for particular task | 2 | 5 | 5 | 20 | team leader | 10/20/2024 | Team members to pushback if you feel like planning is flawed | Current planning goals seem to be ahead of schedule | Open
| lack of management skills | Bad communication and leadership, lacking in work assigning and foreseeing goals and requirements, lacking in team support/training | 3 | 5 | 4 | 12 | team leader | 10/20/2024 | Team member to communicate to leaders in private line regarding their difficulties, issues, or frustration | So far, everyone has something to do | Open
Technology competence | Not familiar with the framework used | Having to learn a new team stack, causing more time needed to complete tasks | 4 | 3 | 1 | 6 | all member | 10/20/2024 | Team members that understand to train/share resources to learn | Not at this stage yet, but when needed Team members can contribute based on the area of expertise | Inactive
| Not familiar with the programming language used | Having to learn a new programming language, causing more time needed to complete tasks | 1 | 4 | 2 | 20 | all member | 10/20/2024 | Team members that understand to train/share resources to learn | Not at this stage yet, but when needed Team members can contribute based on the area of expertise | Inactive
| Not familiar with unit testing | Having to learn how to unit test, causing more time needed to complete tasks | 3 | 1 | 1 | 15 | all member | 10/20/2024 | Team members that understand to train/share resources to learn | Not at this stage yet -- if not learnt when needed other team members can teach or can use ChatGPT to teach how to do unit testing | Inactive
| Other technology incompetence | Having to learn how to use the technology, causing more time needed to complete tasks | 1 | 3 | 1 | 15 | all member | 10/20/2024 | Team members that understand to train/share resources to learn | Using Llama 2 and MongoDB | Open
| Not familiar with Git | Having to learn how to use Git, causing more time needed to complete tasks | 1 | 1 | 1 | 25 | all member | 10/20/2024 | Team members that understand to train/share resources to learn | Team members are familiar with Git | Open
Design and implementation | Improper design | Design does not fit to the purpose of the application or cause inefficiency to the application | 2 | 5 | 5 | 20 | design and implementation leader | 10/20/2024 | Pushback if there are any concerns in the implemented design as soon as possible | So far design seems to be working | Open
| improper technology stack | Technology stack does not fit to the purpose of the application or cause inefficiency to the application | 2 | 5 | 4 | 16 | design and implementation leader | 10/20/2024 | Pushback if there are any concerns in the technology stack as soon as possible | So far technology stack seems to be working | Open
| Messy code | Code is messy without consistent naming convention, comments, and format. This causes team members to take longer time to work together to integrate the different components of the application. | 1 | 4 | 1 | 10 | design and implementation leader | 10/20/2024 | Have team leaders to audit and modify code. Ensure all codes are commented (make habit to overcommunicate your code -- can always erase at the end) | Not at this stage yet | Inactive
Testing | Not enough testing | There are many issues and/or bugs causing error and application crashes | 5 | 5 | 5 | 5 | QA leader | 10/20/2024 | Make a list of implementations to test along with possible errors in input, status, and states that can happen. Run tests based on list | Not at this stage yet | Inactive
Integration and deployment | Not enough time for integration and deployment | Spent too much time in the previous steps or team did not allocate enough time to work on the project, causing setup in meeting the project deadline | 3 | 5 | 5 | 15 | team leader and all members | 10/20/2024 | Stay ahead schedule and add 2 working days margin for setback | Not at this stage yet | Inactive
The team member who is adding the new feature should be the one who determines what is correct for the new functionality that was added.
Work together as a team to make sure each developer has the same environment. This is useful so that there aren't accidental bugs added due to environment issues.

## Iteration 1
This sheet provides some common risks in student projects. You should check if it applies to your group project. You should also feel free to add other risks. Exemplary analysis is also added.
Risk Category | Risk Title | Description | Estimated likelihood of occurrence (L: 1-5 with 1 lowest likelihood) | Estimated Impact (I:1-5 with 1 lowest impact) | Estimated retirement Cost (C: 1-5 with 1 lowest cost) | Priority (lowest number has high priority) (6-L)*(6-I)*C) | Responsible engineer | Target completion date | Detailed plan | Execution summary | Status
personel | Loss team members | One or more team members drop the class | 2 | 4 | 4 | 4*2*4=32 | team leader and all members | 09/20/2024 | Redefine the project scope if necessary, and assign the tasks to other team members. | No one dropped the class so far | Open
| add new team members | A new team member is assigned to group | 1 | 2 | 1 | 20 | team leader and all members | 09/20/2024 | Redefine the project scope if necessary, and assign the tasks to other team members. | No one added to group so far | Open
| Lack of motivation or responsibility | Team members forgot to communicate and complete their task causing setback to team | 4 | 5 | 5 | 10 | team leader and all members | 10/20/2024 | Communicate to team if you expect to be busy for the upcoming week and need help from other team members to complete your task | Everyone active so far | Open
Communication | duplicate work | Lack of communication and clear work division, causing team members to work on the same thing | 2 | 3 | 2 | 24 | team leader and all members | 10/20/2024 | Communicate to team members on discord on what you are working on, make sure that you are using the cloud files for reports and commit/push changes within 30 minutes intervals. | No duplicated work so far | Open
| worked on wrong components | Worked on something that is not needed or assigned to another team member | 4 | 3 | 3 | 18 | team leader and all members | 10/20/2024 | Communicate to team members on discord on what you are working on or talk to team leaders to make sure that you are on the right track. Buddy up with a team member to make sure that you are progressing correctly | Not a problem as for now | Inactive
| useless work | Work on something that does not progress the project further | 4 | 1 | 1 | 10 | team leader and all members | 10/20/2024 | Communicate to team members on discord on what you are working on or talk to team leaders to make sure that you are on the right track. Buddy up with a team member to make sure that you are progressing correctly | Not a problem as for now | Open
| inconsistent work | Team members can't consistently produce same level of work through the project timeline | 5 | 2 | 1 | 4 | team leader and all members | 10/20/2024 | Communicate to team if you expect to be busy for the upcoming week and need help from other team members to complete your task | Not a problem as for now | Open
Requirements | unclear requirements | Requirements were not clear causing team to repeat work on the task. | 2 | 5 | 5 | 20 | team leader | 10/20/2024 | Create a requirements checklist and go through it for every requirement needs. All team members should have the confidence to pushback on unclear or non-relevant requirement | Not a problem as for now | Open
| scope creep | Project's scope increases beyond original plan, this is caused by unclear and poorly defined/controlled scope documentation | 2 | 4 | 3 | 24 | team leader | 10/20/2024 | Create a requirements checklist and go through it for every requirement needs. All team members should have the confidence to pushback on unclear or non-relevant requirement | Not a problem as for now | Open
| constant requirements changes | Requirements for task/work keep changing, causing project direction to constantly change | 3 | 5 | 5 | 15 | team leader | 10/20/2024 | Only allow requirement changes maximum once within an iteration submission | Not a problem as for now | Open
Management | improper task assignments | Assigning work to team members that can't contribute, unbalance workload among team member, bad foresight on task execution time | 2 | 4 | 3 | 24 | team leader | 10/20/2024 | Team members to pushback if you feel like you are incorrectly assigned task | Everything seems to be progressing well and ahead of schedule | Open
| improper planning | Planning wrong, causing repetition in work for particular task | 2 | 5 | 5 | 20 | team leader | 10/20/2024 | Team members to pushback if you feel like planning is flawed | Current planning goals seem to be ahead of schedule | Open
| lack of management skills | Bad communication and leadership, lacking in work assigning and foreseeing goals and requirements, lacking in team support/training | 3 | 5 | 4 | 12 | team leader | 10/20/2024 | Team member to communicate to leaders in private line regarding their difficulties, issues, or frustration | So far, everyone has something to do | Open
Technology competence | Not familiar with the framework used | Having to learn a new team stack, causing more time needed to complete tasks | 4 | 3 | 1 | 6 | all member | 10/20/2024 | Team members that understand to train/share resources to learn | Not at this stage yet, but when needed Team members can contribute based on the area of expertise | Inactive
| Not familiar with the programming language used | Having to learn a new programming language, causing more time needed to complete tasks | 1 | 4 | 2 | 20 | all member | 10/20/2024 | Team members that understand to train/share resources to learn | Not at this stage yet, but when needed Team members can contribute based on the area of expertise | Inactive
| Not familiar with unit testing | Having to learn how to unit test, causing more time needed to complete tasks | 3 | 1 | 1 | 15 | all member | 10/20/2024 | Team members that understand to train/share resources to learn | Not at this stage yet -- if not learnt when needed other team members can teach or can use ChatGPT to teach how to do unit testing | Inactive
| Other technology incompetence | Having to learn how to use the technology, causing more time needed to complete tasks | 1 | 3 | 1 | 15 | all member | 10/20/2024 | Team members that understand to train/share resources to learn | Using Llama 2 and MongoDB | Open
| Not familiar with Git | Having to learn how to use Git, causing more time needed to complete tasks | 1 | 1 | 1 | 25 | all member | 10/20/2024 | Team members that understand to train/share resources to learn | Team members are familiar with Git | Open
Design and implementation | Improper design | Design does not fit to the purpose of the application or cause inefficiency to the application | 2 | 5 | 5 | 20 | team leader and all members | 10/20/2024 | Pushback if there are any concerns in the implemented design as soon as possible | So far design seems to be working | Open
| improper technology stack | Technology stack does not fit to the purpose of the application or cause inefficiency to the application | 2 | 5 | 4 | 16 | team leader and all members | 10/20/2024 | Pushback if there are any concerns in the technology stack as soon as possible | So far technology stack seems to be working | Open
| Messy code | Code is messy without consistent naming convention, comments, and format. This causes team members to take longer time to work together to integrate the different components of the application. | 1 | 4 | 1 | 10 | team leader and all members | 10/20/2024 | Have team leaders to audit and modify code. Ensure all codes are commented (make habit to overcommunicate your code -- can always erase at the end) | Not at this stage yet | Inactive
Testing | Not enough testing | There are many issues and/or bugs causing error and application crashes | 5 | 5 | 5 | 5 | team leader and all members | 10/20/2024 | Make a list of implementations to test along with possible errors in input, status, and states that can happen. Run tests based on list | Not at this stage yet | Inactive
Integration and deployment | Not enough time for integration and deployment | Spent too much time in the previous steps or team did not allocate enough time to work on the project, causing setup in meeting the project deadline | 3 | 5 | 5 | 15 | team leader and all members | 10/20/2024 | Stay ahead schedule and add 2 working days margin for setback | Not at this stage yet | Inactive
The team member who is adding the new feature should be the one who determines what is correct for the new functionality that was added.
Work together as a team to make sure each developer has the same environment. This is useful so that there aren't accidental bugs added due to environment issues.

## Iteration 2
This sheet provides some common risks in student projects. You should check if it applies to your group project. You should also feel free to add other risks. Exemplary analysis is also added.
Risk Category | Risk Title | Description | Estimated likelihood of occurrence (L: 1-5 with 1 lowest likelihood) | Estimated Impact (I:1-5 with 1 lowest impact) | Estimated retirement Cost (C: 1-5 with 1 lowest cost) | Priority (lowest number has high priority) (6-L)*(6-I)*C) | Responsible engineer | Target completion date | Detailed plan | Execution summary | Status
personel | Loss team members | One or more team members drop the class | 2 | 4 | 4 | 4*2*4=32 | team leader and all members | 09/20/2024 | Redefine the project scope if necessary, and assign the tasks to other team members. | No one dropped the class so far | Open
| add new team members | A new team member is assigned to group | 1 | 2 | 1 | 20 | team leader and all members | 09/20/2024 | Redefine the project scope if necessary, and assign the tasks to other team members. | No one added to group so far | Open
| Lack of motivation or responsibility | Team members forgot to communicate and complete their task causing setback to team | 4 | 5 | 5 | 10 | team leader and all members | 10/20/2024 | Communicate to team if you expect to be busy for the upcoming week and need help from other team members to complete your task | Everyone active so far | Open
Communication | duplicate work | Lack of communication and clear work division, causing team members to work on the same thing | 2 | 3 | 2 | 24 | team leader and all members | 10/20/2024 | Communicate to team members on discord on what you are working on, make sure that you are using the cloud files for reports and commit/push changes within 30 minutes intervals. | No duplicated work so far | Open
| worked on wrong components | Worked on something that is not needed or assigned to another team member | 4 | 3 | 3 | 18 | team leader and all members | 10/20/2024 | Communicate to team members on discord on what you are working on or talk to team leaders to make sure that you are on the right track. Buddy up with a team member to make sure that you are progressing correctly | Not a problem as for now | Inactive
| useless work | Work on something that does not progress the project further | 4 | 1 | 1 | 10 | team leader and all members | 10/20/2024 | Communicate to team members on discord on what you are working on or talk to team leaders to make sure that you are on the right track. Buddy up with a team member to make sure that you are progressing correctly | Not a problem as for now | Open
| inconsistent work | Team members can't consistently produce same level of work through the project timeline | 5 | 2 | 1 | 4 | team leader and all members | 10/20/2024 | Communicate to team if you expect to be busy for the upcoming week and need help from other team members to complete your task | Not a problem as for now | Open
Requirements | unclear requirements | Requirements were not clear causing team to repeat work on the task. | 2 | 5 | 5 | 20 | team leader | 10/20/2024 | Create a requirements checklist and go through it for every requirement needs. All team members should have the confidence to pushback on unclear or non-relevant requirement | Not a problem as for now | Open
| scope creep | Project's scope increases beyond original plan, this is caused by unclear and poorly defined/controlled scope documentation | 2 | 4 | 3 | 24 | team leader | 10/20/2024 | Create a requirements checklist and go through it for every requirement needs. All team members should have the confidence to pushback on unclear or non-relevant requirement | Not a problem as for now | Open
| constant requirements changes | Requirements for task/work keep changing, causing project direction to constantly change | 3 | 5 | 5 | 15 | team leader | 10/20/2024 | Only allow requirement changes maximum once within an iteration submission | Not a problem as for now | Open
Management | improper task assignments | Assigning work to team members that can't contribute, unbalance workload among team member, bad foresight on task execution time | 2 | 4 | 3 | 24 | team leader | 10/20/2024 | Team members to pushback if you feel like you are incorrectly assigned task | Everything seems to be progressing well and ahead of schedule | Open
| improper planning | Planning wrong, causing repetition in work for particular task | 2 | 5 | 5 | 20 | team leader | 10/20/2024 | Team members to pushback if you feel like planning is flawed | Current planning goals seem to be ahead of schedule | Open
| lack of management skills | Bad communication and leadership, lacking in work assigning and foreseeing goals and requirements, lacking in team support/training | 3 | 5 | 4 | 12 | team leader | 10/20/2024 | Team member to communicate to leaders in private line regarding their difficulties, issues, or frustration | So far, everyone has something to do | Open
Technology competence | Not familiar with the framework used | Having to learn a new team stack, causing more time needed to complete tasks | 4 | 3 | 1 | 6 | all member | 10/20/2024 | Team members that understand to train/share resources to learn | Not at this stage yet, but when needed Team members can contribute based on the area of expertise | Inactive
| Not familiar with the programming language used | Having to learn a new programming language, causing more time needed to complete tasks | 1 | 4 | 2 | 20 | all member | 10/20/2024 | Team members that understand to train/share resources to learn | Not at this stage yet, but when needed Team members can contribute based on the area of expertise | Inactive
| Not familiar with unit testing | Having to learn how to unit test, causing more time needed to complete tasks | 3 | 1 | 1 | 15 | all member | 10/20/2024 | Team members that understand to train/share resources to learn | Not at this stage yet -- if not learnt when needed other team members can teach or can use ChatGPT to teach how to do unit testing | Inactive
| Other technology incompetence | Having to learn how to use the technology, causing more time needed to complete tasks | 1 | 3 | 1 | 15 | all member | 10/20/2024 | Team members that understand to train/share resources to learn | Using Llama 2 and MongoDB | Open
| Not familiar with Git | Having to learn how to use Git, causing more time needed to complete tasks | 1 | 1 | 1 | 25 | all member | 10/20/2024 | Team members that understand to train/share resources to learn | Team members are familiar with Git | Open
Design and implementation | Improper design | Design does not fit to the purpose of the application or cause inefficiency to the application | 2 | 5 | 5 | 20 | team leader and all members | 10/20/2024 | Pushback if there are any concerns in the implemented design as soon as possible | So far design seems to be working | Open
| improper technology stack | Technology stack does not fit to the purpose of the application or cause inefficiency to the application | 2 | 5 | 4 | 16 | team leader and all members | 10/20/2024 | Pushback if there are any concerns in the technology stack as soon as possible | So far technology stack seems to be working | Open
| Messy code | Code is messy without consistent naming convention, comments, and format. This causes team members to take longer time to work together to integrate the different components of the application. | 1 | 4 | 1 | 10 | team leader and all members | 10/20/2024 | Have team leaders to audit and modify code. Ensure all codes are commented (make habit to overcommunicate your code -- can always erase at the end) | Not at this stage yet | Inactive
Testing | Not enough testing | There are many issues and/or bugs causing error and application crashes | 5 | 5 | 5 | 5 | team leader and all members | 10/20/2024 | Make a list of implementations to test along with possible errors in input, status, and states that can happen. Run tests based on list | Not at this stage yet | Inactive
Integration and deployment | Not enough time for integration and deployment | Spent too much time in the previous steps or team did not allocate enough time to work on the project, causing setup in meeting the project deadline | 3 | 5 | 5 | 15 | team leader and all members | 10/20/2024 | Stay ahead schedule and add 2 working days margin for setback | Not at this stage yet | Inactive
The team member who is adding the new feature should be the one who determines what is correct for the new functionality that was added.
Work together as a team to make sure each developer has the same environment. This is useful so that there aren't accidental bugs added due to environment issues.

## Iteration 3
This sheet provides some common risks in student projects. You should check if it applies to your group project. You should also feel free to add other risks. Exemplary analysis is also added.
Risk Category | Risk Title | Description | Estimated likelihood of occurrence (L: 1-5 with 1 lowest likelihood) | Estimated Impact (I:1-5 with 1 lowest impact) | Estimated retirement Cost (C: 1-5 with 1 lowest cost) | Priority (lowest number has high priority) (6-L)*(6-I)*C) | Responsible engineer | Target completion date | Detailed plan | Execution summary | Status
personel | Loss team members | One or more team members drop the class | 2 | 4 | 4 | 4*2*4=32 | team leader and all members | 09/20/2024 | Redefine the project scope if necessary, and assign the tasks to other team members. | No one dropped the class so far | Open
| add new team members | A new team member is assigned to group | 1 | 2 | 1 | 20 | team leader and all members | 09/20/2024 | Redefine the project scope if necessary, and assign the tasks to other team members. | No one added to group so far | Open
| Lack of motivation or responsibility | Team members forgot to communicate and complete their task causing setback to team | 4 | 5 | 5 | 10 | team leader and all members | 10/20/2024 | Communicate to team if you expect to be busy for the upcoming week and need help from other team members to complete your task | Everyone active so far | Open
Communication | duplicate work | Lack of communication and clear work division, causing team members to work on the same thing | 2 | 3 | 2 | 24 | team leader and all members | 10/20/2024 | Communicate to team members on discord on what you are working on, make sure that you are using the cloud files for reports and commit/push changes within 30 minutes intervals. | No duplicated work so far | Open
| worked on wrong components | Worked on something that is not needed or assigned to another team member | 4 | 3 | 3 | 18 | team leader and all members | 10/20/2024 | Communicate to team members on discord on what you are working on or talk to team leaders to make sure that you are on the right track. Buddy up with a team member to make sure that you are progressing correctly | Not a problem as for now | Inactive
| useless work | Work on something that does not progress the project further | 4 | 1 | 1 | 10 | team leader and all members | 10/20/2024 | Communicate to team members on discord on what you are working on or talk to team leaders to make sure that you are on the right track. Buddy up with a team member to make sure that you are progressing correctly | Not a problem as for now | Open
| inconsistent work | Team members can't consistently produce same level of work through the project timeline | 5 | 2 | 1 | 4 | team leader and all members | 10/20/2024 | Communicate to team if you expect to be busy for the upcoming week and need help from other team members to complete your task | Not a problem as for now | Open
Requirements | unclear requirements | Requirements were not clear causing team to repeat work on the task. | 2 | 5 | 5 | 20 | team leader | 10/20/2024 | Create a requirements checklist and go through it for every requirement needs. All team members should have the confidence to pushback on unclear or non-relevant requirement | Not a problem as for now | Open
| scope creep | Project's scope increases beyond original plan, this is caused by unclear and poorly defined/controlled scope documentation | 2 | 4 | 3 | 24 | team leader | 10/20/2024 | Create a requirements checklist and go through it for every requirement needs. All team members should have the confidence to pushback on unclear or non-relevant requirement | Not a problem as for now | Open
| constant requirements changes | Requirements for task/work keep changing, causing project direction to constantly change | 3 | 5 | 5 | 15 | team leader | 10/20/2024 | Only allow requirement changes maximum once within an iteration submission | Not a problem as for now | Open
Management | improper task assignments | Assigning work to team members that can't contribute, unbalance workload among team member, bad foresight on task execution time | 2 | 4 | 3 | 24 | team leader | 10/20/2024 | Team members to pushback if you feel like you are incorrectly assigned task | Everything seems to be progressing well and ahead of schedule | Open
| improper planning | Planning wrong, causing repetition in work for particular task | 2 | 5 | 5 | 20 | team leader | 10/20/2024 | Team members to pushback if you feel like planning is flawed | Current planning goals seem to be ahead of schedule | Open
| lack of management skills | Bad communication and leadership, lacking in work assigning and foreseeing goals and requirements, lacking in team support/training | 3 | 5 | 4 | 12 | team leader | 10/20/2024 | Team member to communicate to leaders in private line regarding their difficulties, issues, or frustration | So far, everyone has something to do | Open
Technology competence | Not familiar with the framework used | Having to learn a new team stack, causing more time needed to complete tasks | 4 | 3 | 1 | 6 | all member | 10/20/2024 | Team members that understand to train/share resources to learn | Not at this stage yet, but when needed Team members can contribute based on the area of expertise | Inactive
| Not familiar with the programming language used | Having to learn a new programming language, causing more time needed to complete tasks | 1 | 4 | 2 | 20 | all member | 10/20/2024 | Team members that understand to train/share resources to learn | Not at this stage yet, but when needed Team members can contribute based on the area of expertise | Inactive
| Not familiar with unit testing | Having to learn how to unit test, causing more time needed to complete tasks | 3 | 1 | 1 | 15 | all member | 10/20/2024 | Team members that understand to train/share resources to learn | Not at this stage yet -- if not learnt when needed other team members can teach or can use ChatGPT to teach how to do unit testing | Inactive
| Other technology incompetence | Having to learn how to use the technology, causing more time needed to complete tasks | 1 | 3 | 1 | 15 | all member | 10/20/2024 | Team members that understand to train/share resources to learn | Using Llama 2 and MongoDB | Open
| Not familiar with Git | Having to learn how to use Git, causing more time needed to complete tasks | 1 | 1 | 1 | 25 | all member | 10/20/2024 | Team members that understand to train/share resources to learn | Team members are familiar with Git | Open
Design and implementation | Improper design | Design does not fit to the purpose of the application or cause inefficiency to the application | 2 | 5 | 5 | 20 | team leader and all members | 10/20/2024 | Pushback if there are any concerns in the implemented design as soon as possible | So far design seems to be working | Open
| improper technology stack | Technology stack does not fit to the purpose of the application or cause inefficiency to the application | 2 | 5 | 4 | 16 | team leader and all members | 10/20/2024 | Pushback if there are any concerns in the technology stack as soon as possible | So far technology stack seems to be working | Open
| Messy code | Code is messy without consistent naming convention, comments, and format. This causes team members to take longer time to work together to integrate the different components of the application. | 1 | 4 | 1 | 10 | team leader and all members | 10/20/2024 | Have team leaders to audit and modify code. Ensure all codes are commented (make habit to overcommunicate your code -- can always erase at the end) | Not at this stage yet | Inactive
Testing | Not enough testing | There are many issues and/or bugs causing error and application crashes | 5 | 5 | 5 | 5 | team leader and all members | 10/20/2024 | Make a list of implementations to test along with possible errors in input, status, and states that can happen. Run tests based on list | Not at this stage yet | Inactive
Integration and deployment | Not enough time for integration and deployment | Spent too much time in the previous steps or team did not allocate enough time to work on the project, causing setup in meeting the project deadline | 3 | 5 | 5 | 15 | team leader and all members | 10/20/2024 | Stay ahead schedule and add 2 working days margin for setback | Not at this stage yet | Inactive
The team member who is adding the new feature should be the one who determines what is correct for the new functionality that was added.
Work together as a team to make sure each developer has the same environment. This is useful so that there aren't accidental bugs added due to environment issues.

## Final submission
This sheet provides some common risks in student projects. You should check if it applies to your group project. You should also feel free to add other risks. Exemplary analysis is also added.
Risk Category | Risk Title | Description | Estimated likelihood of occurrence (L: 1-5 with 1 lowest likelihood) | Estimated Impact (I:1-5 with 1 lowest impact) | Estimated retirement Cost (C: 1-5 with 1 lowest cost) | Priority (lowest number has high priority) (6-L)*(6-I)*C) | Responsible engineer | Target completion date | Detailed plan | Execution summary | Status
personel | Loss team members | One or more team members drop the class | 2 | 4 | 4 | 4*2*4=32 | team leader and all members | 09/20/2024 | Redefine the project scope if necessary, and assign the tasks to other team members. | No one dropped the class so far | Open
| add new team members | A new team member is assigned to group | 1 | 2 | 1 | 20 | team leader and all members | 09/20/2024 | Redefine the project scope if necessary, and assign the tasks to other team members. | No one added to group so far | Open
| Lack of motivation or responsibility | Team members forgot to communicate and complete their task causing setback to team | 4 | 5 | 5 | 10 | team leader and all members | 10/20/2024 | Communicate to team if you expect to be busy for the upcoming week and need help from other team members to complete your task | Everyone active so far | Open
Communication | duplicate work | Lack of communication and clear work division, causing team members to work on the same thing | 2 | 3 | 2 | 24 | team leader and all members | 10/20/2024 | Communicate to team members on discord on what you are working on, make sure that you are using the cloud files for reports and commit/push changes within 30 minutes intervals. | No duplicated work so far | Open
| worked on wrong components | Worked on something that is not needed or assigned to another team member | 4 | 3 | 3 | 18 | team leader and all members | 10/20/2024 | Communicate to team members on discord on what you are working on or talk to team leaders to make sure that you are on the right track. Buddy up with a team member to make sure that you are progressing correctly | Not a problem as for now | Inactive
| useless work | Work on something that does not progress the project further | 4 | 1 | 1 | 10 | team leader and all members | 10/20/2024 | Communicate to team members on discord on what you are working on or talk to team leaders to make sure that you are on the right track. Buddy up with a team member to make sure that you are progressing correctly | Not a problem as for now | Open
| inconsistent work | Team members can't consistently produce same level of work through the project timeline | 5 | 2 | 1 | 4 | team leader and all members | 10/20/2024 | Communicate to team if you expect to be busy for the upcoming week and need help from other team members to complete your task | Not a problem as for now | Open
Requirements | unclear requirements | Requirements were not clear causing team to repeat work on the task. | 2 | 5 | 5 | 20 | team leader | 10/20/2024 | Create a requirements checklist and go through it for every requirement needs. All team members should have the confidence to pushback on unclear or non-relevant requirement | Not a problem as for now | Open
| scope creep | Project's scope increases beyond original plan, this is caused by unclear and poorly defined/controlled scope documentation | 2 | 4 | 3 | 24 | team leader | 10/20/2024 | Create a requirements checklist and go through it for every requirement needs. All team members should have the confidence to pushback on unclear or non-relevant requirement | Not a problem as for now | Open
| constant requirements changes | Requirements for task/work keep changing, causing project direction to constantly change | 3 | 5 | 5 | 15 | team leader | 10/20/2024 | Only allow requirement changes maximum once within an iteration submission | Not a problem as for now | Open
Management | improper task assignments | Assigning work to team members that can't contribute, unbalance workload among team member, bad foresight on task execution time | 2 | 4 | 3 | 24 | team leader | 10/20/2024 | Team members to pushback if you feel like you are incorrectly assigned task | Everything seems to be progressing well and ahead of schedule | Open
| improper planning | Planning wrong, causing repetition in work for particular task | 2 | 5 | 5 | 20 | team leader | 10/20/2024 | Team members to pushback if you feel like planning is flawed | Current planning goals seem to be ahead of schedule | Open
| lack of management skills | Bad communication and leadership, lacking in work assigning and foreseeing goals and requirements, lacking in team support/training | 3 | 5 | 4 | 12 | team leader | 10/20/2024 | Team member to communicate to leaders in private line regarding their difficulties, issues, or frustration | So far, everyone has something to do | Open
Technology competence | Not familiar with the framework used | Having to learn a new team stack, causing more time needed to complete tasks | 4 | 3 | 1 | 6 | all member | 10/20/2024 | Team members that understand to train/share resources to learn | Not at this stage yet, but when needed Team members can contribute based on the area of expertise | Inactive
| Not familiar with the programming language used | Having to learn a new programming language, causing more time needed to complete tasks | 1 | 4 | 2 | 20 | all member | 10/20/2024 | Team members that understand to train/share resources to learn | Not at this stage yet, but when needed Team members can contribute based on the area of expertise | Inactive
| Not familiar with unit testing | Having to learn how to unit test, causing more time needed to complete tasks | 3 | 1 | 1 | 15 | all member | 10/20/2024 | Team members that understand to train/share resources to learn | Not at this stage yet -- if not learnt when needed other team members can teach or can use ChatGPT to teach how to do unit testing | Inactive
| Other technology incompetence | Having to learn how to use the technology, causing more time needed to complete tasks | 1 | 3 | 1 | 15 | all member | 10/20/2024 | Team members that understand to train/share resources to learn | Using Llama 2 and MongoDB | Open
| Not familiar with Git | Having to learn how to use Git, causing more time needed to complete tasks | 1 | 1 | 1 | 25 | all member | 10/20/2024 | Team members that understand to train/share resources to learn | Team members are familiar with Git | Open
Design and implementation | Improper design | Design does not fit to the purpose of the application or cause inefficiency to the application | 2 | 5 | 5 | 20 | team leader and all members | 10/20/2024 | Pushback if there are any concerns in the implemented design as soon as possible | So far design seems to be working | Open
| improper technology stack | Technology stack does not fit to the purpose of the application or cause inefficiency to the application | 2 | 5 | 4 | 16 | team leader and all members | 10/20/2024 | Pushback if there are any concerns in the technology stack as soon as possible | So far technology stack seems to be working | Open
| Messy code | Code is messy without consistent naming convention, comments, and format. This causes team members to take longer time to work together to integrate the different components of the application. | 1 | 4 | 1 | 10 | team leader and all members | 10/20/2024 | Have team leaders to audit and modify code. Ensure all codes are commented (make habit to overcommunicate your code -- can always erase at the end) | Not at this stage yet | Inactive
Testing | Not enough testing | There are many issues and/or bugs causing error and application crashes | 5 | 5 | 5 | 5 | team leader and all members | 10/20/2024 | Make a list of implementations to test along with possible errors in input, status, and states that can happen. Run tests based on list | Not at this stage yet | Inactive
Integration and deployment | Not enough time for integration and deployment | Spent too much time in the previous steps or team did not allocate enough time to work on the project, causing setup in meeting the project deadline | 3 | 5 | 5 | 15 | team leader and all members | 10/20/2024 | Stay ahead schedule and add 2 working days margin for setback | Not at this stage yet | Inactive
The team member who is adding the new feature should be the one who determines what is correct for the new functionality that was added.
Work together as a team to make sure each developer has the same environment. This is useful so that there aren't accidental bugs added due to environment issues.