## Summary-GroupIterationProgress
This report has 1 group iteration progress summary sheet to be filled at the end of each iteration by the team leader, 1 project ontribution sheet to be filled by everyone at the end of the semester, and 1 weekly report sheet per student.
This sheet should be completed by the team leader (or other member in the team) by the end of each iteration.
iteration | Date range | accomplishment summary (such as user stories/tasks completed/big progress, good practices used, etc) | Technical issues summary | non-technical issues summary | Process improvement/plan | # of user story points completed | # of user story points in progress | # of issues opened | # of issues closed | # of issues remained | Total work time (h) | Total Individual work time (h) | Total group meeting time (h) | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | Any other metrics defined in your SPPP
0 | 09/03-09/12 | Project Ideation, Design, and Flow. Implementation of MongoDB, CI/CD Setup. Start Chatbot Implementation. CI/CD Setup, SpringBoot Setup, Postgresql user dbms setup. Wireframe done. Design decision tree for course building implementation. SPPP version 1. Presentation for Iteration 0. Set up test for Git. Lab1 submission. Created first PR for implementation of CICD. | none identified yet | learning new tech stack for some members | Start setting up spring boot, writing the scripts, and working on the project. | 58 | 113 | 24 | 3 | 21 | 52.16 | 39.66 | 2 | 12.45 | 4.3 | 5.16 | 10.51 | 1 | 4.35 | 4.5
1 | 09/13-09/24 | Finish the implementation of: Chatbot (Overall), coursebuilder, querying basic program and course information, setting best practices, chatbot UI, setting up the Springboot backend, setting up the User-side database using Postgres, Set up the initial of pulling the chat history from Langchain and storing in the user postgres database, finish the docker local environment and setting up CI/CD for AWS deployment, setting up in integrating all components, creating the prompt library for the logic-query mechanism of the chatbot. Planning for Okta authentication and security design element of the project. Applying linting and formatting best practice. Getting use to the PR request before merging to main origin, best practice for auditing and team cooperation. Getting better in working as a team and identified potential communication/weakness in team to fix in future iteration. Getting better at balancing work division among team member. | learning docker and pushing PR to main for some members. | learning docker and pushing PR to main for some members. Documentation is too much that hard to balance between implementation and documentation. Team members start having busy scheduling. Communication and time to integrate different components needs more work -- but will be fixed from experience of working and balance schedules together. | Finish up with the database, Chatbot implementation, SB and React integration, Unit testing, and authentication/security functionality implementation. | 154 | 31 | 102 | 65 | 47 | 154.1 | 151.1 | 3 | 24.3 | 14 | 14.8 | 68 | 6.5 | 18 | 6
2 | 09/25-10/08 | [9 empty] | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3 | 10/09-10/15 | [9 empty] | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[11 empty] | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## projectcontribution
This sheet need to be filled by the end of the semester. You should clearly describe your contribution to the group project in each category in the whole semester.
StudentName | SPPP Document | Requirement Analysis on Pivotaltracker | Design Document (SDD) | Testing Documentation (STD) | Presentation | Implementation (code on Github) | Testing (unittest code on Github or manual testing) | Configuration and Deployment | General communication and management | Other Comments
Natasya Liew
Natthaphon Foithong
Ananya Singh
Battal Cevik
Poom Chantarapornrat
YiJun Liu

## Natasya Liew
The sheet shows an example of a student weekly report. Only include the time that you use to work on the project. Each student should make your own sheet to report your work weekly.
Your Lead Roles: Backup Project Leader, requirement leader
Week # | Date range | Total actual time of this week tasks (h) | Total Individual work time | Total group meeting time | Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | Project Deliverable Contribution | Issues | Issue status or plan | Estimated tasks for next week | Total estimated time
0 | 09/03-09/12 | 9 | 7 | 2 | 0 - Learn about CI/CD and Llama 2 1 - For the Database and Chatbot Mechanism 2 - For the Database, Decision Tree, and Chatbot Mechanism 3 - For the Database 4 - n/a 5 - Team Creation, Environment Setup, Project Ideation, Work Division 6 - Set up Git 7 - n/a | 2 | 1 | 1 | 2 | 0 | 0.5 | 0.5 | 0 | 1. Team creation and communication 2. Project Ideation 3. Set up git, Gdrive, discord notes 4. Meeting Memo 1 and 2 5. SDD write-up: database design, Decision tree algorithm, and Model and Tools section 6. update README.md file 7. Database Design for MongoDB 8. Database creation (for MSSD program only) in MongoDB 9. Contribute to the SPPP: risk mgmt document 10. Work together with Poom for the decision tree and graph of the course builder mechanism | n/a | 1. Create work tickets 2. finish Database design 3. start Decision Tree implementation 4. code the Chatbot implementation/mechanism in Python 5. Oversee teamwork | 3 - Finish MongoDB database, Decision Tree Implementation, and Chatbot Implementation 4 - Test Database and new implementations 5 - Division of Work to build MVP by iteration 1 | 15
1 | 09/13-09/24 | 33 | 30 | 3 | 0 - Learn about JIRA, mermaid/PlantUML, and docker 1 - For the course builder mechanism and more on the Chatbot future iteration 2 - For the Course builder mechanism 3 - For the course builder and integrating with the Chatbot call implementation 4 - course builder and how it interact with the chatbot 5 - Team Creation, Work Division, Coordination with Poom for the Chatbot product and the Springboot team for the integration of database and backend, Battal for the CI/CD, and Natt for collection of input parameters needed to run the coursebuilder implementation. Transition from GitHub actions to JIRA 6 - Set up docker and pushing PR for the newly added features 7 - n/a | 1 | 2 | 3 | 22 | 1 | 3 | 1 | 0 | 1. SPPP Risk mgmt document 2. Team Leader Progress report 3. coursebuilder.py & unittest file for local testing 4. updating JIRA tasks 5. transition from github issue/action to JIRA 6. (Partial) SDD, STD and SPPP update and proofreading. 7. Auditting document files and Poom's chatbot code. 8. Proofreading meeting minutes | 1. UML Diagram took a very long time to redesign everytime I realize a mistake, so I ended up learning mermaid for fast UML Diagram design editing. 2. Docker took awhile to get use to as well. 3. Rushing for time since busy week for teammates and I. 4. Realize that may need more communication between the React, Backend, AI, and SB team for the small details in integrating. Was able to solve last minute but conversation should have been done earlier. | 1. Getting used to docker, especially updating the docker-compose file. 2. Pace better and communicate often. 3. Leave time buffer to before getting back together to team to make sure that issues don't come after too close to the final meeting before compiling everything for the demo. | 1. Work with Poom for our turn in demo and presentation videos, slides and final documentation checks. 2. Creating Implementing the prompt library and logic-query for the chatbot 3. Integrating all the chatbot features with SB/Postgres & Frontend. 4. Decide to keep the current csv rag using Langchain or move to MongoDB with Langchain. 5. Coordinate with Poom and SB team to test and apply lint/format best practice/hygiene | 50
2 | 09/25-10/08
3 | 10/09-10/15

## Ananya Singh
The sheet shows an example of a student weekly report. Only include the time that you use to work on the project. Each student should make your own sheet to report your work weekly.
Your Lead Roles: Backup Project Leader, security lead
Week # | Date range | Total actual time of this week tasks (h) | Total Individual work time | Total group meeting time | Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | Project Deliverable Contribution | Issues | Issue status or plan | Estimated tasks for next week | Total estimated time
0 | 09/03-09/12 | 7 | 5 | 2 | 0 - learned mermaid syntax to build architecture diagram 2 - Designed the architectural flow for our project 5 - present archtectural plan to the team 6 - set up git and project folder structure 7 - prepare presentation | 2 | 0 | 2 | 0 | 0 | 2 | 2 | 2 | 1. Write 3 sections of SPPP 2. Set up git, commit a test message on git Iteration 0 presentation |  | 1. Start working on the spring boot project 2. Create Databases in Postgres 3. Start looking at implementing security 4. Start building JSON API contracts | 5. Build the initial APIs to call the LLM 6. UI should be able to call the API I built | 6
1 | 09/13-09/24 | 23 | 20 | 3 | 0 - Learned how to configure sql2o2 - Learned to how configure everything in docker compose 1 - Created User Stories in JIRA 2 - Design our PostgresSQL Database Model - Designed our JSON API Structure 3 - Built our Spring Boot project - Connected to our Database using Sql2o2 framework - Built our inital APIs for CRUD operations in Database - Created our Domain Models 5 - Communicated our E2E flow for Iteration #1 | 4 | 4 | 5 | 6 | 0 | 4 | 0 | 0 | 1. Created the docker-compose file 2. Lead the project iteration 0 E2E flow 3. Built the spring boot project 4. Design the Database Models and implemented it 5. Architecture Design |  | 1. Can't really say E2E is completed till we connect all the dots (e.g. our ai-service) | 1. Connect with Pooms/Tash's API via Spring Boot project 2. Design chat-history flow along with potential caching scenarios | 15
2 | 09/25-10/08
3 | 10/09-10/15

## Natthaphon Foithong
The sheet shows an example of a student weekly report. Only include the time that you use to work on the project. Each student should make your own sheet to report your work weekly.
Your Lead Roles: Backup Project Leader, requirement leader
Week # | Date range | Total actual time of this week tasks (h) | Total Individual work time | Total group meeting time | Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | Project Deliverable Contribution | Issues | Issue status or plan | Estimated tasks for next week | Total estimated time
0 | 09/03-09/12 | 13.16 | 11.16 | 2 | Individual Task Breakdown 0 - Learning git and github, watching several tutorial 1 - Research and analyzed the best option for user experience 2 - Quick design for low fidelity using crazy 8s methological 3 - Implementation UI design mockup and wireframing with high fidelity using Figma 5 - Discord conversation, a meeting participant and presenting mockup design 6 - Setup personal Git/Github environment | 0.45 | 1.3 | 0.16 | 8 | 0 | 0.15 | 0.3 | 0 | Set up Git, commit to add description for Lab-1 and Delivery mockup UI design | Lack communication and need improvement for agile management | More participante in meeting and start frontend environment for project | 0 - Learning React 3 - Implemention Frontend using React and Bootstap 5 - Prepare for presentation | 15
1 | 09/13-09/24 | 59.6 | 56.6 | 3 | 0 - Learning React + Vite, Docker, Jira, Jest unit testing react, UML diagram and design pattern 1 - Understanding the need for a user-friendly frontend interface, inclduing chat features. Analyzing the stucture for integration between frontend API and Docker. 2 - Final frontend wireframes and mockups for BUAN chatbot using figma, incorpaorationg features like user login, chat interface and UI components. 3 - Developing the React frontend to handle login page and chat interface like chat inputs and display chatBox, buttons, layout and styling. Provides endpoints for frontend to interact with for Chat, course retrieval and history. 4 - Write unit test for frontend UI testing. Conduction load testing on the chat interface and login page. 5 - Regularly updating the team on project milestones and key decisions regarding frontend features. Managing timelines to ensure delivery of UI Components like chat interface, loging page and more. Coordinating with team members acroos different parts of stack to ensure consistency and avoid bottlenecks. Collaborating with Battal for presentation and implementing frontend and backend. 6 - Implementing a CI/CD pipeline for automated deployment and version control using GitHub Action. Set up React + Vite environment and pushing on GitHub to make sure everything work smoothly and not conflig. 7 - Write SDD ducoment and prepare presentation. | 11.3 | 2 | 0.3 | 25 | 3 | 3 | 2 | 13 | 1 - Write 6 sections of SDD 2 - Final wireframes and mockups. 3 - Complete UI component, Chat page and login page. 4 - Write user stroy on Jira and update Jira tasks. | 1 - Git conflig between local and GitHub. 2 - Lack of Docker, UML, Design pattern knowledge cause to spending time on the studying. 3 - VS code issue with git command, could not work well when implement to npm run dev. | Time management, more studying on new programming and tools. | Integration frontend and backend. Work closly to backend developer and more coomunication between the team. | 50
2 | 09/25-10/08
3 | 10/09-10/15

## Battal Cevik
The sheet shows an example of a student weekly report. Only include the time that you use to work on the project. Each student should make your own sheet to report your work weekly.
Your Lead Roles: Backup Project Leader, requirement leader
Week # | Date range | Total actual time of this week tasks (h) | Total Individual work time | Total group meeting time | Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | Project Deliverable Contribution | Issues | Issue status or plan | Estimated tasks for next week | Total estimated time
0 | 09/03-09/12 | 9 | 7 | 2 | Individual Task Breakdown 1 - Learned CICD github actions and writing yml file 2 - Research and analyzed the best option for CICD 3 - Created Pull Request for the Github actions 4 - Research on Llama 2 and design implementation 5 - Creating testing plan and automation 6 - Setup personal Git/Github environment 7 - Study and read all materials | 3 | 1 | 0.5 | 0.5 | 1 | 0.2 | 0.2 | 0.6 | 1 - Created first PR for implementation of CICD 2 - Set up git, commit, and finished lab1 as well 3- Actively participated each meetings and decision for the iteration 0 |  | Finish CICD using github actions Complete QA plan for the project Create Readme file for the project | 1 - Continue learning CICD 2 - Design automation framework for UI and Backend 3 - Implement basic testng for UI and rest assure library for API | 7
1 | 09/13-09/24 | 23 | 20 | 3 | 1- Completed STD documents for testing 2- Learned Docker and created docker file for UI 3- Implemented Docker compose file to the project and fix all problems 4- Research on React + Vite 5- Research on Spring Boot API 6- Created folder structure and architecture of the project in github 7- Prepeare powerpoint for iteration1 and update SDD and other documents | 2 | 3 | 6 | 2 | 2 | 3 | 2 | 3 | 1- Completed folder structure for docker 2- Completed STD for testing 3- Fix the problems regarding running project on docker-compose file 4-Worked on iteration 1 documentation and presentation 5- Worked on video recording for iteration 1 6- Take meeting minutes for this iteration | Docker-compose issues Project folder structure | Fixed all issues regarding docker file and docker compose files Fixed folder structure | Work on AWS EC2 instance Work on deployment process Work on automation testing | 15
2 | 09/25-10/08
3 | 10/09-10/15

## Poom Chantarapornrat
The sheet shows an example of a student weekly report. Only include the time that you use to work on the project. Each student should make your own sheet to report your work weekly.
Your Lead Roles: Backup Project Leader, requirement leader
Week # | Date range | Total actual time of this week tasks (h) | Total Individual work time | Total group meeting time | Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | Project Deliverable Contribution | Issues | Issue status or plan | Estimated tasks for next week | Total estimated time
0 | 09/03-09/12 | 7 | 4.5 | 2.5 | 0 - learn how to use Llama2 in our project, read an article 1 - define first general requirements for the chat bot 2 - draw UML diagrams 5 - participate in the SPPP (requirement section) 6 - set up personal Git/GitHub, set up a requirement tracker tool (GitHub project), and create first user stories | 3 | 1 | 1 | 0 | 0 | 0.5 | 1.5 | 0 | 1. Write the requirement section of the SPPP 2. Set up Git/Github and commit a message to team.md 3. Create UML diagrams for the course reccommendation algorithm and database entities. | 1. not familiar with creating an LLM API, not sure about how to get it work. | 1. Read article and watch YouTube tutorial in a week, be able to find a way to connect the model with a database. | 0 - continue to learn abot Llama2 and HuggingFace API 1 - continue to rehape the requirements as needed 3 - implement the first model API call and test it with the front-end team | 7
1 | 09/13-09/24 | 22.5 | 19.5 | 3 | 0 - learn how to use Langchain, vector store, and API basics 1 - create user stories on Jira for Lab2 2 - create more UML diagrams for lab2 3 - implement Langchain model, create API using FastAPI, Dockerize, test the app 4 - use Postman to test the API calls 5 - participate in the team meeting and take one meeting minutes. Attend 2 informal meetings 6 - configure Python .env for secret API, set up requirements.txt 7 - research open-source and no-cost platforms for the API implementation and found Pinecone, FastAPI, Vercel, and Langserve | 4 | 1 | 0.5 | 12 | 0.5 | 3 | 1 | 0.5 | 1. Write 1 meeting minutes 2. Organize and format the entire SDDD file. Add more information on the AI Application Layer section. 3. Update and add readme.md on GitHub | 1. All chat data in the api is lost because Docker container disposes all app states when it is terminated. 2. Vector store sometimes retrieves incorect class information given a class number. | 1. Integrate the sql data base to read the history data and manage app state using session id. 2. Implement searching by keys to improve the performace. | 0 - learn about key searching 1 - update tasks on Jira more often 3 - implement key searching, database retrieval 4 - test docker container every time before doing a PR 5 - talk to the back-end team about db integration 6. - manage .env file more effectively | 15
2 | 09/25-10/08
3 | 10/09-10/15

## Yujun Liu
The sheet shows an example of a student weekly report. Only include the time that you use to work on the project. Each student should make your own sheet to report your work weekly.
Your Lead Roles: Backup Project Leader, requirement leader
Week # | Date range | Total actual time of this week tasks (h) | Total Individual work time | Total group meeting time | Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | Project Deliverable Contribution | Issues | Issue status or plan | Estimated tasks for next week | Total estimated time
0 | 09/03-09/12 | 7 | 5 | 2 | 0 - learning Spring Boot 2 - backed design 3 - initiated java files 5 - discord conversations | 2 | 0 | 0.5 | 0.01 | 0 | 1 | 0 | 0 | SPPP write ups(all sections besides 3) | 1. need to learn Spring Boot | 1. go learn it on Youtube 2. practice it with better engineers in the team | 1. coding period 2. some deeper design 3. testing | 6
1 | 09/13-09/24 | 7 | 5 | 2 | 0- learning about Spring Boot 3- added basic postgre SQL database 1 - unpdate SPPP 5 - join the weekly meeting and communicate directly with Ananya on SB implementation | 2 | 2 | 0 | 1 | 0 | 2 | 0 | 0 | SPPP write ups | Ready for iteration 2 backend take over | 1. get familiar with implementations from other member 2. align the designs for dbs for next iteration | 1. new db add on | 5
2 | 09/25-10/08
3 | 10/09-10/15