## Summary-GroupIterationProgress
This report has 1 group iteration progress summary sheet to be filled at the end of each iteration by the team leader, 1 project ontribution sheet to be filled by everyone at the end of the semester, and 1 weekly report sheet per student.
This sheet should be completed by the team leader (or other member in the team) by the end of each iteration.
iteration | Date range | accomplishment summary (such as user stories/tasks completed/big progress, good practices used, etc) | Technical issues summary | non-technical issues summary | Process improvement/plan | # of user story points completed | # of user story points in progress | # of issues opened | # of issues closed | # of issues remained | Total work time (h) | Total Individual work time (h) | Total group meeting time (h) | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | Any other metrics defined in your SPPP
0 | 09/03-09/12 | Project Ideation, Design, and Flow. Implementation of MongoDB, CI/CD Setup. Start Chatbot Implementation. CI/CD Setup, SpringBoot Setup, Postgresql user dbms setup. Wireframe done. Design decision tree for course building implementation. SPPP version 1. Presentation for Iteration 0. Set up test for Git. Lab1 submission. Created first PR for implementation of CICD. | none identified yet | learning new tech stack for some members | Start setting up spring boot, writing the scripts, and working on the project. | 58 | 113 | 24 | 3 | 21 | 52.16 | 39.66 | 2 | 12.45 | 4.3 | 5.16 | 10.51 | 1 | 4.35 | 4.5
1 | 09/13-09/24 | Finish the implementation of: Chatbot (Overall), coursebuilder, querying basic program and course information, setting best practices, chatbot UI, setting up the Springboot backend, setting up the User-side database using Postgres, Set up the initial of pulling the chat history from Langchain and storing in the user postgres database, finish the docker local environment and setting up CI/CD for AWS deployment, setting up in integrating all components, creating the prompt library for the logic-query mechanism of the chatbot. Planning for Okta authentication and security design element of the project. Applying linting and formatting best practice. Getting use to the PR request before merging to main origin, best practice for auditing and team cooperation. Getting better in working as a team and identified potential communication/weakness in team to fix in future iteration. Getting better at balancing work division among team member. | learning docker and pushing PR to main for some members. | learning docker and pushing PR to main for some members. Documentation is too much that hard to balance between implementation and documentation. Team members start having busy scheduling. Communication and time to integrate different components needs more work -- but will be fixed from experience of working and balance schedules together. | Finish up with the database, Chatbot implementation, SB and React integration, Unit testing, and authentication/security functionality implementation. | 154 | 31 | 102 | 65 | 47 | 154.1 | 151.1 | 3 | 24.3 | 14 | 14.8 | 68 | 6.5 | 18 | 6
2 | 09/25-10/08 | Updated Documents: SDD, SPPP, SPPP Risk Mgmt, STD, Progress Report, Presentation Slides, Demo video, Presentation Video, Readme.md., Annotation of some codes. Update the dbms and added the complete design and implemented of final db design and code for structural relationship database. Finalize all functionality of the Python AI service chatbot, did not have time to fix the coursebuilder.py code to be less static. Finalize frontend functionality and integrate with the SB backend. Integrated the database and Python AI service with SB. Finalize main functionality of the SB backend (including security and auth). Implemented the SBB testing framework (cucumber), three-tier branch environment (main - stage - develop). | Not enough time to implement Okta Auth, so we switch to JWT Auth. Frontend were way behind compared to the backend services, so Python AI service have to come to frontend after finishing functionality (despite needing to update the coursebuilder.py smells). | Equal work division among members. Communication needs working, but solved in this iteration. Lack of understanding expectation of the final product outlook by team members, solved by scheduling meeting Trevor. | Doing what we can do, communicating with Trevor on the expectations. Having a discord working session together and more experienced members to mentor the younger members and guide in terms what needs to be done. Communicating with each other more often, use other methods outside Discord (call/text). Being comfortable to ask for help early. | 256 | 52 | 149 | 107 | 42 | 298.5 | 200.5 | 25 | 24 | 9 | 14 | 120 | 13 | 64 | 9.5
3 | 10/09-10/15 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[11 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## projectcontribution
This sheet need to be filled by the end of the semester. You should clearly describe your contribution to the group project in each category in the whole semester.
StudentName | SPPP Document | Requirement Analysis on JIRA | Design Document (SDD) | Testing Documentation (STD) | Presentation | Implementation (code on Github) | Testing (unittest code on Github or manual testing) | Configuration and Deployment | General communication and management | Other Comments
Natasya Liew | Responsible in maintaining and revising document. Added the mangement plan and reorganized the requirements according to feedback. | Maintainance and Assigning tasks | Responsible in maintaining and revising document. Did the Database design, Business Logic/Algorithm section. | Filling the documentation in Iteration 1, handing over to Battal at Iteration 2 and 3 | Iteration 2 Presentation slides and video | For Python AI service, database, frontend, and documentation. Along with version release and submission to Blackboard | Unit test for the coursebuilder class, DB testing | Pushing code PR, auditting PR, release version updates, and involved in integration time | Communicating among members to coordinate integration for the product. Allocating work division. Auditting code/Revising documents before submission. Mentoring AJ/Poom in tasks. Coordinating with Battal in JIRA management and team CI/CD needs. Promoting learning among younger members. Communicating with facilitators to gain more understanding on expectations. | Initially part of the Python AI team with Poom while being the Project Manager, after focusing more in coordination and communication to fulfill necessary roles and ensure everybody has a role in the project.
Natthaphon Foithong | Started the initial documentation. | Added his responsibilities | Started the initial documentation. Responsible for the UI Design column. |  | Iteration 1 Demo and Presentation with Battal | For frontend asset, components, and initial set up | Frontend Jest test | Pushing frontend code PR | Coordinate with Poom on the situation on the Frontend development
Ananya Singh | Responsible on Deployment Plan section | Added his responsibilities | Responsible on the security design section. Started the initial write up for the software architecture. | Added examples of SB testing | Iteration 0 Presentation slides, presentation video and Iteration 3 Demo | For all SB codes, auth and security implementation. Coordinating with Tash to design product and process flow. Providing sample codes for API calls for AJ/Poom. Mentoring team on software engineering best standards. | SB test | Pushing code PR, auditting PR, maintain Docker, and involved in the integration team | Work together with Tash as Technical PM and designing the architecture and process for the product. Work with Poom in integrating the end-to-end integration of the product. Collaborated with Battal to ensure Docker works properly and CI/CD process moves smoothly. Mentoring Poom in good software dev habits. | Initial part of the SB team with AJ, but due to AJ not understanding the SB framework, ended up setting up SB backend himself. Work closely with Battal for Deploying in Docker. Work closely with Tash to design end-to-end product and finalizing the tech stack to use.
Battal Cevik | Added content for the Testing, deployment, and CI/CD together with YuJun | Added his responsibilities, assigning members issues for testing and guiding on requirements for testing based on responsible issues | Added a section on CI/CD and Testing Design within the documentation | Started the initial documentation, maintain and revise documentation. | Iteration 1 Demo and Presentation with Natt | For initial frontend assets, components, structure | Main lead on the QA/Testing. Mentoring AJ to apply the frameworks that he set up. Mentoring other team members on industry standards for CI/CD, QA/Testing standards. | Main lead in CI/CD and Deployment | Very good in ensuring that CI/CD and QA/Testing best practice is implemented. Sharp in identifying CI/CD issues and solving it. Worked closely with Ananya to fix the Docker files. Main person maintaining the Github CI/CD. Collaborated with Tash in maintaining JIRA. Mentor AJ in applying tests. | Understands CI/CD, QA, and Testing well. Although work more independently, was very dependable in ensuring QA/Testing, and CI/CD integration was done by industry standards.
Poom Chantarapornrat | Responsible for the Requirement section | Added his responsibilities, maintainance and adding requirements to the latest update of product | Updated some areas on the Python AI service regarding the implementation of Langchain and OpenAI GPT 4.0. Proofread the documentation for iteration 1 | Added some example of Python AI service testing | Iteration 2 Demo and readme docs | For Python AI service and frontend components, actions, and integration(provided most code) | Python AI service, Frontend testing | Pushing the iteration 0 update. PR code and audit PR. And involved in integration team | Carried the team in most code development and integration work. Collaborated closely with Tash on the Python AI service, Ananya on the SB integrations, Natt in joining the frontend team. | Very hardworking, willing to put in effort to write code in a short time to ensure product delivery back to scheduled timing. Learning React overnight in order to support the Frontend needs through Codeacademy. Often work with Ananya and Tash in Discord sprint work sessions on weekdays and weekend from morning to around 2-3am to delivery product and integrate.
YuJun Liu | Started the initial documentation. Update the Deployment Plan. | Added his responsibilities | Responsible in updating the Class diagram and software architecture section | Added some examples for API testing | Iteration 3 Presentation slides and video | For Linting/Formatting | Support Battal to add unittests | Ensuring Linting/Formatting rules in GitHub. | Communicated difficulty, allowing members to mentor/guide iteration 1 onwards | Very eager learner, willing to accept feedback and joins Discord Sprint work sessions.

## Natasya Liew
The sheet shows an example of a student weekly report. Only include the time that you use to work on the project. Each student should make your own sheet to report your work weekly.
Your Lead Roles: Team Leader
Week # | Date range | Total actual time of this week tasks (h) | Total Individual work time | Total group meeting time | Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | Project Deliverable Contribution | Issues | Issue status or plan | Estimated tasks for next week | Total estimated time
0 | 09/03-09/12 | 9 | 7 | 2 | 0 - Learn about CI/CD and Llama 2 1 - For the Database and Chatbot Mechanism 2 - For the Database, Decision Tree, and Chatbot Mechanism 3 - For the Database 4 - n/a 5 - Team Creation, Environment Setup, Project Ideation, Work Division 6 - Set up Git 7 - n/a | 2 | 1 | 1 | 2 | 0 | 0.5 | 0.5 | 0 | 1. Team creation and communication 2. Project Ideation 3. Set up git, Gdrive, discord notes 4. Meeting Memo 1 and 2 5. SDD write-up: database design, Decision tree algorithm, and Model and Tools section 6. update README.md file 7. Database Design for MongoDB 8. Database creation (for MSSD program only) in MongoDB 9. Contribute to the SPPP: risk mgmt document 10. Work together with Poom for the decision tree and graph of the course builder mechanism | n/a | 1. Create work tickets 2. finish Database design 3. start Decision Tree implementation 4. code the Chatbot implementation/mechanism in Python 5. Oversee teamwork | 3 - Finish MongoDB database, Decision Tree Implementation, and Chatbot Implementation 4 - Test Database and new implementations 5 - Division of Work to build MVP by iteration 1 | 15
1 | 09/13-09/24 | 33 | 30 | 3 | 0 - Learn about JIRA, mermaid/PlantUML, and docker 1 - For the course builder mechanism and more on the Chatbot future iteration 2 - For the Course builder mechanism 3 - For the course builder and integrating with the Chatbot call implementation 4 - course builder and how it interact with the chatbot 5 - Team Creation, Work Division, Coordination with Poom for the Chatbot product and the Springboot team for the integration of database and backend, Battal for the CI/CD, and Natt for collection of input parameters needed to run the coursebuilder implementation. Transition from GitHub actions to JIRA 6 - Set up docker and pushing PR for the newly added features 7 - n/a | 1 | 2 | 3 | 22 | 1 | 3 | 1 | 0 | 1. SPPP Risk mgmt document 2. Team Leader Progress report 3. coursebuilder.py & unittest file for local testing 4. updating JIRA tasks 5. transition from github issue/action to JIRA 6. (Partial) SDD, STD and SPPP update and proofreading. 7. Auditting document files and Poom's chatbot code. 8. Proofreading meeting minutes | 1. UML Diagram took a very long time to redesign everytime I realize a mistake, so I ended up learning mermaid for fast UML Diagram design editing. 2. Docker took awhile to get use to as well. 3. Rushing for time since busy week for teammates and I. 4. Realize that may need more communication between the React, Backend, AI, and SB team for the small details in integrating. Was able to solve last minute but conversation should have been done earlier. | 1. Getting used to docker, especially updating the docker-compose file. 2. Pace better and communicate often. 3. Leave time buffer to before getting back together to team to make sure that issues don't come after too close to the final meeting before compiling everything for the demo. | 1. Work with Poom for our turn in demo and presentation videos, slides and final documentation checks. 2. Creating Implementing the prompt library and logic-query for the chatbot 3. Integrating all the chatbot features with SB/Postgres & Frontend. 4. Decide to keep the current csv rag using Langchain or move to MongoDB with Langchain. 5. Coordinate with Poom and SB team to test and apply lint/format best practice/hygiene | 50
2 | 09/25-10/08 | 95 | 65 | 25 | 0 - Refreshing on React, Redux, API calls 1 - For the database 2 - For the database with Ananya, with Poom implementing the rest of the Python AI service (increasing the scope of chatbot ability) 3 - For the database, collaborate with Poom for frontend react and finalizing the full functionality of the Python AI service. Drafting the Python AI service scripts to add for Poom's code (suggestions through chat). 4 - For the database and frontend react, along with integration with Ananya and Poom, then with Battal supported by AJ. Implementation for the full functionality of the Python AI service 5 - Coordinating among different divisions, mostly with Ananya this week to integrate the database with SB. Coordinating closely with Poom to finish up our Python AI service functionality, then after to take over the implementation of the front-end. Integrating the Python AI service, to SB, database, and frontend React. Ensuring all teams can integrate their parts together into a whole product. 6 - Pushing new PR, auditting some PR codes. 7 - Annotating some codes and Revising the SDD, SPPP, SPPP risk, Presentation slides documents, collecting information from the BU MET Website and compiling everything into a promptlib.json file to pass to Poom. Updating the JIRA documents. Reviewing meeting minutes and codes to ensure everything is connected. | 1 | 1 | 1 | 45 | 1 | 10 | 1 | 35 | 1. Documents: SPPP Risk mgmt document, SDD, SPPP, Progress Report Team Leader, Meeting Minutes 6 and Revisions, Presentation Slide Update. 2. Presentation Video 3. JIRA update 4. promptlib.json file that was ethically `scrapped` from the BU MET website 5. code suggestion for the Chatbot script 6. updates on the frontend codes 7. the updates in the db .sql files along with designing the final ideal relational dbms. 8. Communication/Mgmt role heavy this week. | 1. Getting back to pace after realizing that the Frontend needs alot of support to finish in time. 2. Coordinating with the microteam to integrate the process and communicate the vision of the final product with all members. 3. Work division based on members' capability 4. Envisioning the Expectation of Stakeholders' on the final product deliverables. 5. Meeting the accepted quality of deliverables. 6. Balancing the number of features and scope based on the limited time left for the project. 7. Switching between roles to get back to schedule. | 1. Setting up meeting with Trevor for the team to understanding expectation and purpose of tasks. 2. Survival mode - do as much possible to delivery a complete product by the end of the iteration. 3. Putting more hours to ensure everything is up-to-date, working, and all members are informed to objectives. 4. Taking over leftover tasks after allocating every member their tasks. 5. Mentoring members that need more guidance. | 1. Final update on the documentations, prepping AJ to present the last presentation video. 2. Reattempt to make the code for the coursebuilder.py file for the courseTree implementation to be less static. 3. Linting/Formatting. 4. Additional Testing/QA Audits. 5. Communication/Management. | 15
3 | 10/09-10/15

## Ananya Singh
The sheet shows an example of a student weekly report. Only include the time that you use to work on the project. Each student should make your own sheet to report your work weekly.
Your Lead Roles: Backup Project Leader, security lead
Week # | Date range | Total actual time of this week tasks (h) | Total Individual work time | Total group meeting time | Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | Project Deliverable Contribution | Issues | Issue status or plan | Estimated tasks for next week | Total estimated time
0 | 09/03-09/12 | 7 | 5 | 2 | 0 - learned mermaid syntax to build architecture diagram 2 - Designed the architectural flow for our project 5 - present archtectural plan to the team 6 - set up git and project folder structure 7 - prepare presentation | 2 | 0 | 2 | 0 | 0 | 2 | 2 | 2 | 1. Write 3 sections of SPPP 2. Set up git, commit a test message on git Iteration 0 presentation |  | 1. Start working on the spring boot project 2. Create Databases in Postgres 3. Start looking at implementing security 4. Start building JSON API contracts | 5. Build the initial APIs to call the LLM 6. UI should be able to call the API I built | 6
1 | 09/13-09/24 | 23 | 20 | 3 | 0 - Learned how to configure sql2o2 - Learned to how configure everything in docker compose 1 - Created User Stories in JIRA 2 - Design our PostgresSQL Database Model - Designed our JSON API Structure 3 - Built our Spring Boot project - Connected to our Database using Sql2o2 framework - Built our inital APIs for CRUD operations in Database - Created our Domain Models 5 - Communicated our E2E flow for Iteration #1 | 4 | 4 | 5 | 6 | 0 | 4 | 0 | 0 | 1. Created the docker-compose file 2. Lead the project iteration 0 E2E flow 3. Built the spring boot project 4. Design the Database Models and implemented it
2 | 09/25-10/08 | 80 | 55 | 25 | 0 - Learned about JWT Token Generation in Spring Boot and how to add filters in every rest call 1 - Database changes 2 - Redesigned Database changes design 3 - Added JWT Token Generation to Spring Boot Project - Finished all required APIs - Altered the DAO to account for DB changes - Fixed all the dockerfiles to FINALLY have an E2E flow - Every API call requires JWT token - Joined the front-end side and added the changes required for JWT Token - Fixed a few bugs in the front-end project 5 - Led with Tash to communicate our DB changes and all of our API changes 6 - Fixed all environent and configuration issues including Dockerfile | 5 | 5 | 5 | 35 | 0 | 25 | 5 | 0 | 1. Added JWT Token Generation to Spring Boot Project 2. Finished all required APIs in the spring boot project 3. Altered the DAO to account for DB changes 4. Fixed all the dockerfiles to FINALLY have an E2E flow 5. Every API call requires JWT token 6. Joined the front-end side and added the changes required for JWT Token 7. Fixed a few bugs in the front-end project 8. Contributed to SPPP and SDD for security | none | 1. Everything works locally now E2E so now I will focus on this week on making everything work on AWS! 2. Fix any outstanding bugs or defects 3. Increase unit test coverage in springboot | 1. AWS e2e | 20
3 | 10/09-10/15

## Natthaphon Foithong
The sheet shows an example of a student weekly report. Only include the time that you use to work on the project. Each student should make your own sheet to report your work weekly.
Your Lead Roles: Backup Project Leader, Design Leader
Week # | Date range | Total actual time of this week tasks (h) | Total Individual work time | Total group meeting time | Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | Project Deliverable Contribution | Issues | Issue status or plan | Estimated tasks for next week | Total estimated time
0 | 09/03-09/12 | 13.16 | 11.16 | 2 | Individual Task Breakdown 0 - Learning git and github, watching several tutorial 1 - Research and analyzed the best option for user experience 2 - Quick design for low fidelity using crazy 8s methological 3 - Implementation UI design mockup and wireframing with high fidelity using Figma 5 - Discord conversation, a meeting participant and presenting mockup design 6 - Setup personal Git/Github environment | 0.45 | 1.3 | 0.16 | 8 | 0 | 0.15 | 0.3 | 0 | Set up Git, commit to add description for Lab-1 and Delivery mockup UI design | Lack communication and need improvement for agile management | More participante in meeting and start frontend environment for project | 0 - Learning React 3 - Implemention Frontend using React and Bootstap 5 - Prepare for presentation | 15
1 | 09/13-09/24 | 59.6 | 56.6 | 3 | 0 - Learning React + Vite, Docker, Jira, Jest unit testing react, UML diagram and design pattern 1 - Understanding the need for a user-friendly frontend interface, inclduing chat features. Analyzing the stucture for integration between frontend API and Docker. 2 - Final frontend wireframes and mockups for BUAN chatbot using figma, incorpaorationg features like user login, chat interface and UI components. 3 - Developing the React frontend to handle login page and chat interface like chat inputs and display chatBox, buttons, layout and styling. Provides endpoints for frontend to interact with for Chat, course retrieval and history. 4 - Write unit test for frontend UI testing. Conduction load testing on the chat interface and login page. 5 - Regularly updating the team on project milestones and key decisions regarding frontend features. Managing timelines to ensure delivery of UI Components like chat interface, loging page and more. Coordinating with team members acroos different parts of stack to ensure consistency and avoid bottlenecks. Collaborating with Battal for presentation and implementing frontend and backend. 6 - Implementing a CI/CD pipeline for automated deployment and version control using GitHub Action. Set up React + Vite environment and pushing on GitHub to make sure everything work smoothly and not conflig. 7 - Write SDD ducoment and prepare presentation. | 11.3 | 2 | 0.3 | 25 | 3 | 3 | 2 | 13 | 1 - Write 6 sections of SDD 2 - Final wireframes and mockups. 3 - Complete UI component, Chat page and login page. 4 - Write user stroy on Jira and update Jira tasks. | 1 - Git conflig between local and GitHub. 2 - Lack of Docker, UML, Design pattern knowledge cause to spending time on the studying. 3 - VS code issue with git command, could not work well when implement to npm run dev. | Time management, more studying on new programming and tools. | Integration frontend and backend. Work closly to backend developer and more communication between the team. | 50
2 | 09/25-10/08 | 32 | 28 | 4 | 0 - Learning Integration Okta authentication 1 - Understanding the need for a user-friendly frontend interface, inclduing chat features. Analyzing the stucture for integration between frontend API and Docker. 2 - Update frontend wireframes and mockups, adding feature like new signup page and New user profile. 3 - Build a new user profile page. Implement dowload function 5 - Regularly updating the team on project milestones. Coordinating with team members across different parts of stack to ensure consistency and avoid bottlenecks. Collaborating with Requirement leader and Configuration leader that they jump right to help implementation frontend api and functionaliies. 7 - Update UI component and class diagram on SDD ducoment. Formatting all documentations. | 5 | 0 | 6 | 9 | 0 | 4 | 0 | 8 | 1 - Update SDD and formatting all documantations. 2 - Update wireframes and mockups. 3 - New user profile page and download functional | Miss communication with the team and lack of motivation of work | Being more active and motivate. More contribution with member. | Learn testing and Working with QA leader and implement unit test for frontend. Help other member if their need. | 15-20
3 | 10/09-10/15

## Battal Cevik
The sheet shows an example of a student weekly report. Only include the time that you use to work on the project. Each student should make your own sheet to report your work weekly.
Your Lead Roles: Backup Project Leader, QA leader
Week # | Date range | Total actual time of this week tasks (h) | Total Individual work time | Total group meeting time | Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | Project Deliverable Contribution | Issues | Issue status or plan | Estimated tasks for next week | Total estimated time
0 | 09/03-09/12 | 9 | 7 | 2 | Individual Task Breakdown 1 - Learned CICD github actions and writing yml file 2 - Research and analyzed the best option for CICD 3 - Created Pull Request for the Github actions 4 - Research on Llama 2 and design implementation 5 - Creating testing plan and automation 6 - Setup personal Git/Github environment 7 - Study and read all materials | 3 | 1 | 0.5 | 0.5 | 1 | 0.2 | 0.2 | 0.6 | 1 - Created first PR for implementation of CICD 2 - Set up git, commit, and finished lab1 as well 3- Actively participated each meetings and decision for the iteration 0 |  | Finish CICD using github actions Complete QA plan for the project Create Readme file for the project | 1 - Continue learning CICD 2 - Design automation framework for UI and Backend 3 - Implement basic testng for UI and rest assure library for API | 7
1 | 09/13-09/24 | 23 | 20 | 3 | 1- Completed STD documents for testing 2- Learned Docker and created docker file for UI 3- Implemented Docker compose file to the project and fix all problems 4- Research on React + Vite 5- Research on Spring Boot API 6- Created folder structure and architecture of the project in github 7- Prepeare powerpoint for iteration1 and update SDD and other documents | 2 | 3 | 6 | 2 | 2 | 3 | 2 | 3 | 1- Completed folder structure for docker 2- Completed STD for testing 3- Fix the problems regarding running project on docker-compose file 4-Worked on iteration 1 documentation and presentation 5- Worked on video recording for iteration 1 6- Take meeting minutes for this iteration | Docker-compose issues Project folder structure | Fixed all issues regarding docker file and docker compose files Fixed folder structure | Work on AWS EC2 instance Work on deployment process Work on automation testing | 15
2 | 09/25-10/08 | 33 | 25 | 8 | 0-Set up the environment and maven for testing 1-Created BDD test automation framework 2-Created UI Tests using selenium cucumber 3-Created API test using rest assue 4-Research on deployment AWS EC2 5-Deploy the application on AWS EC2 6-Worked on linting issues and fixed 7-Mentoring team members for QA/CICD process and worked on documentation | 2 | 2 | 2 | 2 | 5 | 15 | 3 | 2 | -Completed all required documents -Deployed the application to the AWS EC2 -Created Test Automation Framework -Started adding regression test suite -Set up test environment, branches, linting, CICD | -Deployment on E2C instance using docker -Maven dependencies issues for testing framework -Deploying Selenium grid for UI testing -Set up local environment to run regression suite -Linting issues and failing PRs | Fixed EC2 instance issues Fix selenium grid issues Fixed local set up and maven | Adding more test cases on the regression suite Complete all documents Complete all testing requirements Complete E2E testing Continue monitor CICD for deployment Worked on linting and updating and refactoring code Mentoring team member regarding industry standards on QA | 30
3 | 10/09-10/15

## Poom Chantarapornrat
The sheet shows an example of a student weekly report. Only include the time that you use to work on the project. Each student should make your own sheet to report your work weekly.
Your Lead Roles: Backup Project Leader, requirement leader
Week # | Date range | Total actual time of this week tasks (h) | Total Individual work time | Total group meeting time | Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | Project Deliverable Contribution | Issues | Issue status or plan | Estimated tasks for next week | Total estimated time
0 | 09/03-09/12 | 7 | 4.5 | 2.5 | 0 - learn how to use Llama2 in our project, read an article 1 - define first general requirements for the chat bot 2 - draw UML diagrams 5 - participate in the SPPP (requirement section) 6 - set up personal Git/GitHub, set up a requirement tracker tool (GitHub project), and create first user stories | 3 | 1 | 1 | 0 | 0 | 0.5 | 1.5 | 0 | 1. Write the requirement section of the SPPP 2. Set up Git/Github and commit a message to team.md 3. Create UML diagrams for the course reccommendation algorithm and database entities. | 1. not familiar with creating an LLM API, not sure about how to get it work. | 1. Read article and watch YouTube tutorial in a week, be able to find a way to connect the model with a database. | 0 - continue to learn abot Llama2 and HuggingFace API 1 - continue to rehape the requirements as needed 3 - implement the first model API call and test it with the front-end team | 7
1 | 09/13-09/24 | 22.5 | 19.5 | 3 | 0 - learn how to use Langchain, vector store, and API basics 1 - create user stories on Jira for Lab2 2 - create more UML diagrams for lab2 3 - implement Langchain model, create API using FastAPI, Dockerize, test the app 4 - use Postman to test the API calls 5 - participate in the team meeting and take one meeting minutes 6 - configure Python .env for secret API, set up requirements.txt 7 - research open-source and no-cost platforms for the API implementation and found Pinecone, FastAPI, Vercel, and Langserve | 4 | 1 | 0.5 | 12 | 0.5 | 3 | 1 | 0.5 | 1. Write 1 meeting minutes 2. Organize and format the entire SDDD file. Add more information on the AI Application Layer section. 3. Update and add readme.md on GitHub | 1. All chat data in the api is lost because Docker container disposes all app states when it is terminated. 2. Vector store sometimes retrieves incorect class information given a class number. | 1. Integrate the sql data base to read the history data and manage app state using session id. 2. Implement searching by keys to improve the performace. | 0 - learn about key searching 1 - update tasks on Jira more often 3 - implement key searching, database retrieval 4 - test docker container every time before doing a PR 5 - talk to the back-end team about db integration 6. - manage .env file more effectively | 15
2 | 09/25-10/08 | 43.5 | 18.5 | 25 | 0 - learned Langchain Agent and React.js 3 - implemented Langchain agent to automatically classifies user requests. Implemented React's statemanagement using Context API, Created a form for user to fill in course information. 4 - tested the Langchain agent using unittest in Python 5 - met with the backend team to integrate the ai-service API, met with the frontend team to perform state management and service integrations 6 - update the requirement.txt file to clean up unused Python packages. | 8 | 0 | 0 | 29 | 2 | 4 | 0.5 | 0 | 1. updated requirement analysis for the SPPP 2. updated the ai-service section in the SDD 3. delivered the Langchain agent code to the repo 4. delivered the React.js state management to the repo 5. delivered the profile form UI to the repo 6. delivered the demo video | 1. managing state for a big application is complex. 2. not familair with React/Redux | 1. Implement a more robust state management like Redux 2. Spend more time learning Redux | 0 - learn redux 1 - update any requirement changes 3 - implement Redux to the app 4 - test the state manage code 5 - attend all meetings 6 - add Redux lib to package.json | 30
3 | 10/09-10/15

## Yujun Liu
The sheet shows an example of a student weekly report. Only include the time that you use to work on the project. Each student should make your own sheet to report your work weekly.
Your Lead Roles: Backup Project Leader, configuration leader
Week # | Date range | Total actual time of this week tasks (h) | Total Individual work time | Total group meeting time | Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | Project Deliverable Contribution | Issues | Issue status or plan | Estimated tasks for next week | Total estimated time
0 | 09/03-09/12 | 7 | 5 | 2 | 0 - learning Spring Boot 2 - backed design 3 - initiated java files 5 - discord conversations | 2 | 0 | 0.5 | 0.01 | 0 | 1 | 0 | 0 | SPPP write ups(all sections besides 3) | 1. need to learn Spring Boot | 1. go learn it on Youtube 2. practice it with better engineers in the team | 1. coding period 2. some deeper design 3. testing | 6
1 | 09/13-09/24 | 7 | 5 | 2 | 0- learning about Spring Boot 3- added basic postgre SQL database 1 - unpdate SPPP 5 - join the weekly meeting and communicate directly with Ananya on SB implementation | 2 | 2 | 0 | 1 | 0 | 2 | 0 | 0 | SPPP write ups | Ready for iteration 2 backend take over | 1. get familiar with implementations from other member 2. align the designs for dbs for next iteration | 1. new db add on | 5
2 | 09/25-10/08 | 15 | 9 | 6 | 0 - learning about unit testing and functional testing 0 - learning about linting and CI process integration 1 - code base study and structure 2 - front end design meetings 4 - unit testing and functional testing 5 - team meetings and conversation via chat | 3 | 1 | 0 | 0 | 5 | 6 | 0 | 0 | updated structure diagram and data flow diagram updated SDD software strucure and SPPP deployment plan discussed and troubleshooting for front end team implemented unit testing and function testing with QA team | 1. need to spend more time figure out more scenarios about functional testing 2. finish all unit testing 3. fix lint rules asap | go spend more time on it | more unit testing, and functional testing. contribute to code base more to collaborate with team | 30
3 | 10/09-10/15